## Slide 1: 08 Modernizationtimeline
UIAO Modernization Program

## Slide 2: UIAO Modernization Timeline

## Slide 3: 1. Title Page
Field | Value
Version | 1.0
Date | March 2026
Classification | CUI/FOUO
Source Planes | Identity, Network, Addressing, Telemetry, Security, Management
Document Type | Program Timeline (01_Canon)

## Slide 4: 2. Purpose
This document defines the official modernization timeline for the Unified Identity-Addressing-Overlay (UIAO) program. It sequences identity, network, addressing, telemetry, security, and governance modernization activities into a coherent, dependency-aware, leadership-ready plan aligned with Zero Trust, TIC 3.0, and FedRAMP 20x.

## Slide 5: 3. Scope
Included
Six-month modernization timeline
Workstream sequencing (A-D)
Dependencies across control planes
Milestones, deliverables, and readiness gates
Alignment with federal mandates
Excluded
Detailed project plans (covered in appendices)
Vendor-specific deployment instructions
Budget and acquisition details

## Slide 6: 4. Control Plane Alignment
The modernization timeline spans all six UIAO control planes:
Plane | Timeline Role
Identity | First modernization priority; foundation for all others
Network | Cloud-first routing, segmentation, DIA, INR
Addressing | Deterministic IPAM, DNS/DHCP modernization
Telemetry and Location | Real-time signals for routing, security, compliance
Security and Compliance | TIC 3.0, Zero Trust, FedRAMP 20x
Management | Drift detection, CMDB, device compliance

## Slide 7
The timeline ensures each plane is modernized in the correct order.

## Slide 8: 5. Core Concepts
The modernization timeline operationalizes the Seven Core Concepts:
Conversation as the atomic unit
Identity as the root namespace
Deterministic addressing
Certificate-anchored overlay
Telemetry as control
Embedded governance and automation
Public service first
These concepts guide sequencing and prioritization.

## Slide 9: 6. Architecture Model
6.1 Workstream Overview
The modernization program is divided into four coordinated workstreams:
Workstream A — Identity Modernization
Entra ID
MFA/SSPR
Conditional Access
ICAM governance
PIM
Device trust
Workstream B — Network Modernization
Cisco Catalyst SD-WAN
Cloud OnRamp for M365
DIA
INR
Identity-aware segmentation
Workstream C — Addressing Modernization
Infoblox IPAM
DNS/DHCP modernization
Cloud/on-prem reconciliation
Deterministic addressing
Workstream D — Telemetry and Governance
M365 Network Telemetry
SD-WAN telemetry
Endpoint telemetry
ServiceNow CMDB
Intune compliance
TIC 3.0 Cloud + Branch
These workstreams operate in parallel but with strict dependency ordering.

## Slide 10: 7. Runtime Model
The timeline follows the UIAO runtime model:
7.1 Conversation Flow
Identity - Addressing - Certificates - Overlay - Telemetry - Policy
7.2 Deterministic Sequencing
Identity modernization must precede:
Addressing modernization
Network segmentation
Telemetry correlation
Zero Trust enforcement
7.3 Continuous Evaluation
Telemetry integration begins early and matures throughout the timeline.

## Slide 11: 8. Modernization Timeline (6 Months)
Below is the canonical, dependency-aware modernization timeline.
Month 1 — Foundations (HLD Phase)
Identity
Entra ID HLD
MFA/SSPR readiness
Identity lifecycle mapping
Network
SD-WAN HLD
Cloud OnRamp design
INR architecture
Addressing
IPAM HLD
DNS/DHCP discovery
Addressing inventory
Telemetry
M365 Network Telemetry HLD
SD-WAN telemetry design
Governance
CMDB baseline
Drift detection framework
Milestone: All HLDs approved.
Month 2 — Configuration (LLD Phase)
Identity
Conditional Access LLD
PIM configuration
Identity governance policies
Network
SD-WAN LLD
DIA design
Segmentation policy draft
Addressing
DNS/DHCP LLD
Cloud IPAM integration design
Telemetry
Location inference (IPAM + SD-WAN)
E911 readiness design
Governance
CMDB enrichment
Intune compliance baseline
Milestone: All LLDs approved.
Month 3 — Initial Deployment
Identity
MFA/SSPR rollout
Conditional Access enforcement
Identity governance activation
Network
DIA pilot
SD-WAN pilot
Cloud OnRamp activation
Addressing
Cloud IPAM pilot
DNS/DHCP modernization pilot
Telemetry
M365 telemetry ingestion
SD-WAN telemetry ingestion
Governance
CMDB reconciliation
Intune compliance enforcement
Milestone: Identity and network pilots operational.
Month 4 — Expansion
Identity
Full Conditional Access rollout
PIM enforcement
Network
Segmentation rollout
INR integration
DIA expansion
Addressing
Deterministic addressing rollout
DNS/DHCP modernization expansion
Telemetry
Conversation-level correlation
Location inference activation
Governance
Drift detection automation
ServiceNow change workflows
Milestone: Identity-aware routing operational.
Month 5 — Integration
Identity
ICAM governance maturity
Identity assurance tuning
Network
Identity-aware segmentation
SD-WAN optimization
Addressing
IPAM automation
Cloud/on-prem reconciliation
Telemetry
SIEM integration
CDM/CLAW integration
Governance
Continuous Authorization (CA-7)
Automated remediation
Milestone: Full telemetry integration.
Month 6 — Compliance and Readiness
Identity
NIST 800-63 alignment
Identity assurance validation
Network
TIC 3.0 Cloud Use Case
TIC 3.0 Branch Use Case
Addressing
Deterministic addressing validation
DNS/DHCP modernization complete
Telemetry
KSI generation
FedRAMP 20x evidence readiness
Governance
CMDB authoritative
Drift-resistant operations
Milestone: FedRAMP 20x Phase 2 readiness.

## Slide 12: 9. Dependencies and Sequencing
Upstream Dependencies
Identity modernization
IPAM modernization
SD-WAN overlay deployment
Downstream Dependencies
TIC 3.0 packages
FedRAMP 20x evidence generation
Leadership reporting
Critical Path
Identity - Addressing - Network - Telemetry - Governance - Compliance

## Slide 13: 10. Governance and Drift Controls
Source of Authority
HR — identity lifecycle
Network architecture — addressing
PKI — certificate trust
System owners — configuration baselines
Drift Detection
CMDB reconciliation
Intune compliance
SD-WAN overlay validation
IPAM reconciliation
Remediation Workflow
Automated ServiceNow change
Conditional Access enforcement
Certificate renewal
IPAM correction

## Slide 14: 11. Appendices
Appendix A: Definitions
See docs/glossary.md
Appendix B: Tables
Control Plane Alignment table is in Section 4. Modernization Timeline is in Section 8.
Appendix C: Diagram References
See docs/images/ for all referenced architecture diagrams.
Appendix D: Evidence Sources
See data/parameters.yml and control-library entries for evidence source catalogs.

## Slide 15: 12. Revision History
Version | Date | Author | Summary
1.0 | 2026-03 | UIAO Canon Engine | Initial canonical release