# Modernization Program - Integrated Timeline (Gantt-Style)

Covers Workstreams A-D Format: Markdown table (PMO-ready) Status: Ready for scheduling import

## 1. Overview

This timeline represents the full modernization program across:

- Identity (Entra ID + ICAM)

- Network (Cisco Catalyst SD-WAN)

- Addressing (InfoBlox IPAM)

- Telemetry + Location Services

Each phase is aligned to dependencies and sequencing across workstreams.

## 2. Timeline Summary (6 months Program)

| Phase | Workstream | Milestone | Duration | Dependencies |
| --- | --- | --- | --- | --- |

M1 | A | Entra ID Baseline Complete | Month 1 | None |

M1 | B | SD-WAN HLD Complete | Month 1 | None |

M1 | C | IPAM HLD Complete | Month 1 | None |

M1 | D | Telemetry HLD Complete | Month 1 | None |

M2 | A | Conditional Access Baseline | Month 2 | M1-A |

M2 | B | SD-WAN LLD Complete | Month 2 | M1-B |

M2 | C | DNS/DHCP Modernization Plan | Month 2 | M1-C |

M2 | D | Location Services Modernization Plan | Month 2 | M1-D |

M3 | A | MFA/SSPR Modernization | Month 3 | M2-A |

M3 | B | DIA Pilot Branches Live | Month 3 | M2-B |

M3 | B | Cloud OnRamp for M365 Pilot | Month 3 | M2-B |

M3 | C | Cloud IPAM Reconciliation | Month 3 | M2-C |

M3 | D | E911 Dynamic Location Mapping | Month 3 | M2-D |

M3 | D | IPAM-Based Location Inference | Month 3 | M2-D, M3-C |

M4 | A | PIM + Access Reviews | Month 4 | M3-A |

M4 | B | Segmentation Baseline Deployed | Month 4 | M3-B |

M4 | B | SD-WAN Telemetry Export Operational | Month 4 | M3-B |

M4 | C | IPAM > SD-WAN Integration | Month 4 | M3-C |

M4 | C | IPAM > Telemetry Integration | Month 4 | M3-C |

M4 | D | M365 Network Telemetry Integrated | Month 4 | M3-D |

M5 | A | ICAM Governance Package | Month 5 | M4-A |

M5 | B | Identity-Aware Routing Integration | Month 5 | M4-B, M4-A |

M5 | C | Addressing Governance Approved | Month 5 | M4-C |

M5 | D | TIC 3.0 Cloud Use Case Package | Month 5 | M4-D |

M6 | A | Identity > Telemetry Integration | Month 6 | M5-A |

M6 | B | INR Readiness Complete | Month 6 | M5-B |

M6 | C | IPAM Lifecycle Automation | Month 6 | M5-C |

M6 | D | TIC 3.0 Branch Use Case Package | Month 6 | M5-D |

M6 | D | CDM/CLAW Integration | Month 6 | M5-D |

## 3. Workstream Summary

### Workstream A: Identity (Entra ID + ICAM)

| Month | Deliverable |
| --- | --- |

1 | Entra ID Baseline Complete |

2 | Conditional Access Baseline |

3 | MFA/SSPR Modernization |

4 | PIM + Access Reviews |

5 | ICAM Governance Package |

6 | Identity > Telemetry Integration |

### Workstream B: Network (Cisco Catalyst SD-WAN)

| Month | Deliverable |
| --- | --- |

1 | SD-WAN HLD Complete |

2 | SD-WAN LLD Complete |

3 | DIA Pilot Branches Live |

3 | Cloud OnRamp for M365 Pilot |

4 | Segmentation Baseline Deployed |

4 | SD-WAN Telemetry Export Operational |

5 | Identity-Aware Routing Integration |

6 | INR Readiness Complete |

### Workstream C: Addressing (InfoBlox IPAM)

| Month | Deliverable |
| --- | --- |

1 | IPAM HLD Complete |

2 | DNS/DHCP Modernization Plan |

3 | Cloud IPAM Reconciliation |

4 | IPAM > SD-WAN Integration |

4 | IPAM > Telemetry Integration |

5 | Addressing Governance Approved |

6 | IPAM Lifecycle Automation |

### Workstream D: Telemetry + Location Services

| Month | Deliverable |
| --- | --- |

1 | Telemetry HLD Complete |

2 | Location Services Modernization Plan |

3 | E911 Dynamic Location Mapping |

3 | IPAM-Based Location Inference |

4 | M365 Network Telemetry Integrated |

5 | TIC 3.0 Cloud Use Case Package |

6 | TIC 3.0 Branch Use Case Package |

6 | CDM/CLAW Integration |

Generated from UIAO data layer - March 2026